## Timeline Proyek
No | Minggu | Tanggal Mulai | Tanggal Selesai | Fase | Kategori | Task | Deskripsi | PIC | Status | Prioritas | Milestone | Catatan
1 | Weekly #1 | 11/05/2026 | 17/05/2026 | Planning & Setup | Project Management | Setup GitHub Repository | Inisialisasi repo private; buat struktur folder; setup .gitignore; buat branch strategy | Project Manager | Belum Mulai | Tinggi | Repo & Environment Siap
2 | Weekly #1 | 11/05/2026 | 17/05/2026 | Planning & Setup | Project Management | Koordinasi Tim Minggu 1 | Memimpin weekly sync perdana; bahas pembagian tugas; setup Google Calendar | Project Manager | Belum Mulai | Tinggi | Repo & Environment Siap
3 | Weekly #1 | 11/05/2026 | 17/05/2026 | Planning & Setup | AI/ML | Pengumpulan Dataset | Mengumpulkan dataset hate speech & abusive language dari GitHub dan Kaggle | AI/ML Engineer | Belum Mulai | Tinggi | Repo & Environment Siap
4 | Weekly #1 | 11/05/2026 | 17/05/2026 | Planning & Setup | AI/ML | EDA (Exploratory Data Analysis) | Menganalisis distribusi label; panjang teks; frekuensi kata; potensi bias dataset | AI/ML Engineer | Belum Mulai | Tinggi | Repo & Environment Siap
5 | Weekly #1 | 11/05/2026 | 14/05/2026 | Planning & Setup | AI/ML | Relabeling Dataset (Awal) | Mengonversi label multi-kelas ke 2 kelas biner: PANTAS dan TIDAK PANTAS | AI/ML Engineer | Belum Mulai | Tinggi | Repo & Environment Siap
6 | Weekly #1 | 11/05/2026 | 17/05/2026 | Planning & Setup | Backend | Setup FastAPI Project | Inisialisasi FastAPI; struktur folder; virtual environment; konfigurasi .env | Backend Developer | Belum Mulai | Tinggi | Repo & Environment Siap
7 | Weekly #1 | 11/05/2026 | 17/05/2026 | Planning & Setup | Backend | Desain Database Schema | Merancang schema tabel: users; messages; rooms; violations (SQLAlchemy) | Backend Developer | Belum Mulai | Tinggi | Repo & Environment Siap
8 | Weekly #1 | 11/05/2026 | 17/05/2026 | Planning & Setup | Frontend | Setup React Project | Inisialisasi React (Vite) + Tailwind CSS; konfigurasi folder components/pages/services | Frontend Developer | Belum Mulai | Tinggi | Repo & Environment Siap
9 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | AI/ML | Preprocessing Teks | Lowercasing; hapus URL/emoji; normalisasi slang; tokenisasi | AI/ML Engineer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
10 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | AI/ML | Split Dataset | Membagi data train/validation/test (70/15/15) dengan stratified split | AI/ML Engineer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
11 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | AI/ML | Relabeling Dataset (Finalisasi) | Finalisasi konversi label; pastikan semua bahasa kasar masuk TIDAK PANTAS | AI/ML Engineer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
12 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | AI/ML | Fine-tuning IndoBERT (Iterasi 1) | Melatih indobert-base-p1 binary classification (PyTorch + HuggingFace) | AI/ML Engineer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
13 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Backend | Endpoint POST /api/messages | Menerima pesan dari FE; panggil AI inference; simpan ke DB; return respons | Backend Developer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
14 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Backend | Endpoint GET /api/messages/{room_id} | Mengambil riwayat pesan sebuah room dengan pagination | Backend Developer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
15 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Backend | WebSocket /ws/{room_id} (Awal) | Mulai membangun koneksi WebSocket real-time antar pengguna | Backend Developer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
16 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Backend | Validasi & Keamanan | CORS setup; validasi input; sanitasi teks sebelum dikirim ke model | Backend Developer | Belum Mulai | Sedang | IndoBERT Iterasi 1 & API Moderasi
17 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Frontend | Komponen ChatBubble | Pesan 2 varian: normal (PANTAS) atau tersembunyi (TIDAK PANTAS) | Frontend Developer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
18 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Frontend | Komponen ChatInput | Input teks dengan tombol kirim; validasi input tidak kosong | Frontend Developer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
19 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Frontend | Komponen ChatHeader | Header ruang chat (nama grup; jumlah anggota aktif) | Frontend Developer | Belum Mulai | Sedang | IndoBERT Iterasi 1 & API Moderasi
20 | Weekly #2 | 18/05/2026 | 24/05/2026 | Development | Frontend | Halaman Login | Form memilih nama pengguna simulasi sebelum masuk room chat | Frontend Developer | Belum Mulai | Sedang | IndoBERT Iterasi 1 & API Moderasi
21 | Weekly #2 | 18/05/2026 | 21/05/2026 | Development | Frontend | Halaman ChatRoom (Awal) | Gabungkan komponen chat; kelola state pesan; scroll otomatis | Frontend Developer | Belum Mulai | Tinggi | IndoBERT Iterasi 1 & API Moderasi
22 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | AI/ML | Evaluasi Model | Hitung Accuracy/Precision/Recall/F1; Confusion Matrix; kalibrasi threshold | AI/ML Engineer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
23 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | AI/ML | Optimasi Model | Tuning hyperparameter; augmentasi data jika F1 < 82% | AI/ML Engineer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
24 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | AI/ML | Inference Function | Buat predict(text) -> {label, confidence} untuk dipanggil backend | AI/ML Engineer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
25 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | AI/ML | Streamlit Demo Endpoint | Demo interaktif: input teks -> label + confidence + visualisasi metrik | AI/ML Engineer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
26 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | AI/ML | Simpan & Dokumentasi Model | Upload model ke Google Drive; dokumentasikan di README | AI/ML Engineer | Belum Mulai | Sedang | Model Final & Streamlit Demo
27 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | Backend | Integrasi AI ke Backend | Muat model ke memori saat server start; panggil inference tiap pesan | Backend Developer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
28 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | Backend | Logika Aksi Moderasi | PANTAS -> normal; TIDAK PANTAS -> sembunyikan + notifikasi + log | Backend Developer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
29 | Weekly #3 | 25/05/2026 | 28/05/2026 | Development & Integration | Backend | WebSocket (Finalisasi) | Finalisasi dan uji WebSocket real-time stabil | Backend Developer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
30 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | Frontend | Halaman ChatRoom (Final) | Finalisasi integrasi komponen chat dengan WebSocket | Frontend Developer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
31 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | Frontend | Integrasi WebSocket (FE) | Hubungkan FE ke WebSocket BE untuk pesan real-time | Frontend Developer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
32 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | Frontend | Notifikasi Moderasi (FE) | Pesan edukatif untuk pengirim saat pesannya disembunyikan | Frontend Developer | Belum Mulai | Tinggi | Model Final & Streamlit Demo
33 | Weekly #3 | 25/05/2026 | 31/05/2026 | Development & Integration | Frontend | Halaman RoomList | Daftar room/grup tersedia untuk dipilih pengguna | Frontend Developer | Belum Mulai | Sedang | Model Final & Streamlit Demo
34 | Weekly #4 | 01/06/2026 | 07/06/2026 | Integration & Testing | Project Management | Koordinasi Integrasi & Testing | Pimpin integrasi FE-BE-AI; tulis test case; koordinasi bug fixing | Project Manager | Belum Mulai | Tinggi | Integrasi Penuh & CP2 (3 Jun)
35 | Weekly #4 | 01/06/2026 | 03/06/2026 | Integration & Testing | Project Management | Laporan Kemajuan PIJAK | Submit laporan kemajuan ke PIJAK (DEADLINE: 3 Juni 2026) | Project Manager | Belum Mulai | Tinggi | Integrasi Penuh & CP2 (3 Jun)
36 | Weekly #4 | 01/06/2026 | 07/06/2026 | Integration & Testing | Backend | Endpoint Admin | GET /api/admin/violations dan GET /api/admin/stats | Backend Developer | Belum Mulai | Tinggi | Integrasi Penuh & CP2 (3 Jun)
37 | Weekly #4 | 01/06/2026 | 07/06/2026 | Integration & Testing | Backend | Testing & Dokumentasi API | Unit test; .env.example; dokumentasi API (auto-docs) | Backend Developer | Belum Mulai | Sedang | Integrasi Penuh & CP2 (3 Jun)
38 | Weekly #4 | 01/06/2026 | 04/06/2026 | Integration & Testing | Frontend | Halaman AdminDashboard | Log pelanggaran + grafik statistik (pie/bar chart) | Frontend Developer | Belum Mulai | Tinggi | Integrasi Penuh & CP2 (3 Jun)
39 | Weekly #4 | 01/06/2026 | 07/06/2026 | Integration & Testing | Frontend | Integrasi Penuh FE-BE | Hubungkan semua komponen FE dengan endpoint API BE | Frontend Developer | Belum Mulai | Tinggi | Integrasi Penuh & CP2 (3 Jun)
40 | Weekly #4 | 01/06/2026 | 07/06/2026 | Integration & Testing | All Team | Testing Integrasi FE-BE-AI | Uji alur end-to-end: kirim pesan -> moderasi -> respons -> tampilan | All Team | Belum Mulai | Tinggi | Integrasi Penuh & CP2 (3 Jun)
41 | Weekly #5 | 08/06/2026 | 14/06/2026 | Finalization | Project Management | README Documentation | Dokumentasi instalasi; cara menjalankan; link model; referensi dataset | Project Manager | Belum Mulai | Tinggi | Submission Final (19 Jun)
42 | Weekly #5 | 08/06/2026 | 16/06/2026 | Finalization | Project Management | Project Brief PIJAK | Susun Project Brief sesuai template PIJAK | Project Manager | Belum Mulai | Tinggi | Submission Final (19 Jun)
43 | Weekly #5 | 14/06/2026 | 18/06/2026 | Finalization | Project Management | Slide Presentasi | Slide PPTX/PDF: latar belakang; solusi; demo; hasil evaluasi | Project Manager | Belum Mulai | Tinggi | Submission Final (19 Jun)
44 | Weekly #5 | 14/06/2026 | 18/06/2026 | Finalization | Project Management | Video Presentasi | Rekam video 10 menit YouTube; semua anggota presentasi | Project Manager | Belum Mulai | Tinggi | Submission Final (19 Jun)
45 | Weekly #5 | 08/06/2026 | 16/06/2026 | Finalization | Project Management | Panduan Penggunaan | PDF atau video tutorial penggunaan aplikasi | Project Manager | Belum Mulai | Sedang | Submission Final (19 Jun)
46 | Weekly #5 | 08/06/2026 | 14/06/2026 | Finalization | All Team | Testing End-to-End | Pengujian menyeluruh termasuk edge case | All Team | Belum Mulai | Tinggi | Submission Final (19 Jun)
47 | Weekly #5 | 12/06/2026 | 17/06/2026 | Finalization | All Team | Bug Fixing | Perbaikan semua bug dari fase testing | All Team | Belum Mulai | Tinggi | Submission Final (19 Jun)
48 | Weekly #5 | 08/06/2026 | 15/06/2026 | Finalization | Frontend | Responsif Design | Pastikan tampilan baik di mobile (>=375px) dan desktop | Frontend Developer | Belum Mulai | Sedang | Submission Final (19 Jun)
49 | Weekly #5 | 18/06/2026 | 19/06/2026 | Submission | All Team | Final Submission | Submit semua deliverable (DEADLINE: 19 Juni 2026) | All Team | Belum Mulai | Tinggi | Submission Final (19 Jun)

## Milestone
No | Minggu | Tanggal | Target Pencapaian | Deadline Penting | Progress (%)
1 | Weekly #1 | 11-17 Mei 2026 | Setup repo; dataset terkumpul; EDA selesai; skeleton FastAPI & React jalan |  | 0
2 | Weekly #2 | 18-24 Mei 2026 | IndoBERT iterasi pertama; endpoint API moderasi berfungsi; komponen chat UI selesai |  | 0
3 | Weekly #3 | 25-31 Mei 2026 | Model dievaluasi & dioptimasi; WebSocket berfungsi; Streamlit demo online; integrasi AI-BE |  | 0
4 | Weekly #4 | 1-7 Juni 2026 | Integrasi penuh FE-BE-AI; dashboard admin berfungsi; laporan kemajuan PIJAK | 3 Juni - Laporan PIJAK | 0
5 | Weekly #5 | 8-19 Juni 2026 | Testing E2E; bug fixing; README; Project Brief; slide; video presentasi | 19 Juni - DEADLINE FINAL | 0

## Gantt Chart
Task | PIC | 11/05 | 12/05 | 13/05 | 14/05 | 15/05 | 16/05 | 17/05 | 18/05 | 19/05 | 20/05 | 21/05 | 22/05 | 23/05 | 24/05 | 25/05 | 26/05 | 27/05 | 28/05 | 29/05 | 30/05 | 31/05 | 01/06 | 02/06 | 03/06 | 04/06 | 05/06 | 06/06 | 07/06 | 08/06 | 09/06 | 10/06 | 11/06 | 12/06 | 13/06 | 14/06 | 15/06 | 16/06 | 17/06 | 18/06 | 19/06
Setup GitHub Repository | Project Manager
Koordinasi Tim Minggu 1 | Project Manager
Pengumpulan Dataset | AI/ML Engineer
EDA (Exploratory Data Analysis) | AI/ML Engineer
Relabeling Dataset (Awal) | AI/ML Engineer
Setup FastAPI Project | Backend Developer
Desain Database Schema | Backend Developer
Setup React Project | Frontend Developer
Preprocessing Teks | AI/ML Engineer
Split Dataset | AI/ML Engineer
Relabeling Dataset (Finalisasi) | AI/ML Engineer
Fine-tuning IndoBERT (Iterasi 1) | AI/ML Engineer
Endpoint POST /api/messages | Backend Developer
Endpoint GET /api/messages/{room_id} | Backend Developer
WebSocket /ws/{room_id} (Awal) | Backend Developer
Validasi & Keamanan | Backend Developer
Komponen ChatBubble | Frontend Developer
Komponen ChatInput | Frontend Developer
Komponen ChatHeader | Frontend Developer
Halaman Login | Frontend Developer
Halaman ChatRoom (Awal) | Frontend Developer
Evaluasi Model | AI/ML Engineer
Optimasi Model | AI/ML Engineer
Inference Function | AI/ML Engineer
Streamlit Demo Endpoint | AI/ML Engineer
Simpan & Dokumentasi Model | AI/ML Engineer
Integrasi AI ke Backend | Backend Developer
Logika Aksi Moderasi | Backend Developer
WebSocket (Finalisasi) | Backend Developer
Halaman ChatRoom (Final) | Frontend Developer
Integrasi WebSocket (FE) | Frontend Developer
Notifikasi Moderasi (FE) | Frontend Developer
Halaman RoomList | Frontend Developer
Koordinasi Integrasi & Testing | Project Manager
Laporan Kemajuan PIJAK | Project Manager
Endpoint Admin | Backend Developer
Testing & Dokumentasi API | Backend Developer
Halaman AdminDashboard | Frontend Developer
Integrasi Penuh FE-BE | Frontend Developer
Testing Integrasi FE-BE-AI | All Team
README Documentation | Project Manager
Project Brief PIJAK | Project Manager
Slide Presentasi | Project Manager
Video Presentasi | Project Manager
Panduan Penggunaan | Project Manager
Testing End-to-End | All Team
Bug Fixing | All Team
Responsif Design | Frontend Developer
Final Submission | All Team